## Progress Planning and Tracking
Project Name: | WM-3 Intelligent Robot Arm
Report Date: | Dec 2nd, 2024
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | Understand and be familiar with software |  |  |  | Design and Finish software |  |  |  | Apply software to hardware and make it works |  |  |  | ########
[5 empty] | 8/26/2024 | 9/3/2024 | 9/9/2024 | 9/16/2024 | 9/23/2024 | 9/30/2024 | 10/7/2024 | 10/14/2024 | 10/21/2024 | 10/28/2024 | 11/4/2024 | 11/11/2024
Requirements | Meeting with Prof. Majeed | 100% |  | Ellie, Zhiwen | 1 | 2 | 2
| Decide software and requirements. | 100% |  | Ellie, Zhiwen | 4.5
| Review requirements with Prof. | 100% |  | Ellie, Zhiwen | 0.5
| Get sign off on requirements (team meeting) | 100% |  | Ellie, Zhiwen | 1 | 0.8 | 1
Project design | Install tech required * |  |  | Ellie, Zhiwen |  | 3.5 | 5
| Hardware design |  |  | Ellie, Zhiwen |  | 2.5
X design
Y design
Develop working prototype
Test prototype
Development | Review prototype design
Apply to hardware and check
Document updated design
Test product
Final report | Presentation preparation
Poster preparation
Final report submission to D2L and project owner
|  |  | Total work hours | 23.8 | 7 | 8.8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours